## Slide 1: 2023-2026 Corporate Strategic Plan Year 3 (2025) Annual Progress Report
Presented To: Township Council
Presented On: Monday April 13, 2026
Presented By: Alex Pinheiro, Strategic Policy Coordinator

## Slide 2: Agenda
Governance Framework
Performance Accountability in King
Framework for Evaluating Strategic Progress: Objectives & Key Results
Strategic Performance Summary
Strategic Performance Highlights
Communications Plan
2025 CSP Progress Dashboard

## Slide 3: Governance Framework
Community Vision & Mission
Corporate Mission, Vision & Values and Corporate Strategic Plan
.
Departmental Plans, Frameworks & Initiatives
Multi-Year Operational & Capital Planning
.
Council
Staff

## Slide 4
Term of Council
Corporate Strategic Plan / Service Budget
Daily
Employee Work Plans
Medium to Long Term
Official Plan, Master Plans and Frameworks
Annual
Budget & Business Plans
Corporate Planning Frameworks and Performance Accountability
Strategic Performance
Objectives and Key Results (OKR)
Operational Service Performance
Results Based Accountability (RBA)

## Slide 5
Framework for Measuring & Evaluating Strategic Performance

## Slide 6: Objectives & Key Results (OKR)
Objective Key Results (OKR) Framework
Performance Measurement of Strategic Plans in Local Government
Accountability and Transparency of Strategic Performance
Qualitative & Quantitative Reporting
Reported Annually in Q2
Measure What Matters – John Doerr

## Slide 7
Objectives & Key Results (OKR)
Priority AREAs defines the area of focus for strategic changes to be realized through implementation of the plan
Objectives What do we want to achieve?
KEY RESULTS THE RESULTS THAT TELL US IF WE HAVE ACHIEVED OUR OBJECTIVE
ACTIONS WHAT WE ARE DOING TO ACHIEVE OUR KEY RESULTS
DEVELOPING THE PLAN
REPORTING
ON THE PLAN
We will [objective] as measured by [key results]

## Slide 8
Objectives & Key Results (OKR) - Example
Priority AREAs BE MORE ACTIVE
Objectives RUN THE SOUTHLAKE 5K
KEY RESULTS Run 2 KM a day for 2 months WALK 5 km a week for 2 months LIFT WEIGHTS 2X a WEEK for 2 months
ACTIONS Plan a 2km & 5km route CREATE A WEIGHT ROUTINE SET TRAINING ALARMS
DEVELOPING THE PLAN
REPORTING
ON THE PLAN
We will [objective] as measured by [key results]

## Slide 9: Objectives & Key Results (OKR)
A Greener Future
Mitigate Climate Change
KR 1
KR 2
KR 3
KR 4
Promote Tree Canopy Growth
KR 1
KR 2
KR 3
KR 4
Sustainable Asset Management
Develop Asset Funding Strategies
KR 1
KR 2
KR 3
KR 4
Improve Capital Assets
KR 1
KR 2
KR 3
KR 4
Complete Communities
Manage Growth to Best Serve King
KR 1
KR 2
KR 3
KR 4
Enrich Community Well-Being
KR 1
KR 2
KR 3
KR 4
Service Excellence
Increase Data Driven Decision Making
KR 1
KR 2
KR 3
KR 4
Enhance Service Experience
KR 1
KR 2
KR 3
KR 4
THE GOALS WE WANT TO ACHIEVE RELATED TO EACH PRIORITY
A RESULT THAT
MEASURES THE
PROGRESS OF
EACH GOAL
THE TOP STRATEGIC PRIORITIES IDENTIFIED BY COUNCIL
KEY RESULTS
OBJECTIVES
PRIORITY AREAS
9

## Slide 10
2025 Annual Progress Report

## Slide 11: Strategic Performance Report Summary
29 Key Results
Percentage Towards Completion
Actions Undertaken
Status

## Slide 12: CSP Performance Report Summary
A Greener Future
Complete Communities
Service Excellence
Sustainable Asset Management
Key Results Status Summary
Legend
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.41 | 0.48 | 0 | 0.07 | 0.04
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.14 | 0.72 | 0 | 0.14 | 0
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.25 | 0.62 | 0 | 0 | 0.13
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.57 | 0.29 | 0.14 | 0
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.71 | 0.29 | 0 | 0 | 0

## Slide 13: Highlights by Priority Area

## Slide 14: A GREENER FUTURE

## Slide 15
Develop environmentally sustainable solutions to reduce King's footprint and mitigate against the impacts of climate change.
Adopt and Begin the Implementation of the Community Climate Change Action Plan 2026.
Reduce Corporate Emissions by 140 Tco2E (tonnes of carbon dioxide).
Develop a Green Development Standards Incentive Program by 2026.
Chart: 
| Complete | In Progress
Sales | 90 | 10
☑ Advanced implementation of the King Community Climate Action Plan following Council endorsement
☑ Expanded the King Environmental Action Team and Foodcycler Program
Chart: 
| Complete | In Progress
Sales | 75 | 25
☑ Reviewed incentives driving the ThinKING Green Sustainable Development Program
☑ Completed a Jurisdictional Scan of Incentives in other Local Municipalities
☑ Received Council direction, defined non-financial incentive framework
100%
PROCEEDING AS PLANNED
COMPLETED
PROCEEDING AS PLANNED
☑ Supported opening of the Zancor Center, achieving the Zero Carbon Building Design Certification
☑ Launched a corporate composting program across municipal facilities
☑ Advanced corporate energy tracking and emissions analysis

## Slide 16
Promote Tree Canopy Growth and Enhance Natural Lands
Inventory all Township Natural Assets by 2026.
Develop an Invasive Species Management Strategy by 2026.
Plant 50,000 trees, shrubs and wildflowers.
Chart: 
| Complete | In Progress
Sales | 80 | 20
☑ Completed an Invasive Species Management Strategy for internal review
☑ Contributed to King’s Green Development Standards Program
☑ Managed 3,298m² of invasive species impacted areas in 2025
Achieve the York Region minimum canopy cover recommendation for King of 36%.
☑ Began implementation of the King Technical Forest Study
☑ Identified new restoration locations for plantings in 2026
☑ Leveraged grant funds to maximize planting activities
PROCEEDING AS PLANNED
PROCEEDING AS PLANNED
PROCEEDING AS PLANNED
UNDER REVIEW
Chart: 
| Category 1
Complete | 80
In Progress | 20
20%
80%
☑ Applied & Secured external Funding from Greenbelt Foundation
☑ Engaged an external consultant to advance Natural Asset Inventory
☑ Obtained and reviewed natural asset GIS datasets to inform deliverables
Chart: 
|
Complete | 29665
Outstanding | 20335
☑ 13,831 plantings in 2025
☑ Engaged 736 volunteers over 1,183 hours to support planting activities
97%
3%
59%
*40,000*

## Slide 17: SUSTAINABLE ASSET MANAGEMENT

## Slide 18
Develop asset funding strategies which ensure long term fiscal sustainability.
Implement a Stormwater Charge by 2023.
☑ Key Result completed in 2023 reporting year
Create and Implement an Asset-Funding strategy by 2025.
Finalize and Implement the Asset Management Program by 2025.
☑ Completed Phase 2 of the core Asset Management Program
☑ Incorporated the following into a Comprehensive Asset Management Plan:
Phase 1 (non-core assets) & Phase 2 (core-assets)
Asset Management Funding Strategy
Capital Asset Levels of Service
COMPLETE
COMPLETE
☑ Reviewed financial assumptions associated with proposed service levels to assess long-term affordability
☑ Finalized the Asset-Funding Strategy as part of the 2025 Comprehensive Asset Management Plan
Chart: 
| Category 1
Complete | 100
100%
COMPLETE
100%
Chart: 
| Category 1
Complete | 100

## Slide 19
Improve our capital assets (transportation, environmental, facilities and parks) for continued community use and enjoyment.
Develop and Implement a Stormwater Monitoring and Maintenance Strategy by 2026.
Update (5) asset-related Master Plans & Strategies by 2025.
Establish the levels of service for all capital assets by 2025.
☑ Developed the Stormwater Operations and Maintenance Manual to define Township standards
☑ Started pond clean-outs using risk-based prioritization metrics
☑ Strengthened internal capacity through training and a new Environmental Technologist
Chart: 
| Complete | In Progress
Sales | 70 | 30
Develop an Asset Disposition Strategy by 2025.
PROCEEDING AS PLANNED

## Slide 20
Fall 2025 Pond Clean-Out

## Slide 21
Improve our capital assets (transportation, environmental, facilities and parks) for continued community use and enjoyment.
Develop and Implement a Stormwater Monitoring and Maintenance Strategy by 2026.
Update (5) asset-related Master Plans & Strategies by 2025.
Establish the levels of service for all capital assets by 2025.
☑ Developed the Stormwater Operations and Maintenance Manual to define Township standards
☑ Started pond clean-outs using risk-based prioritization metrics
☑ Strengthened internal capacity through training and a new Environmental Technologist
Chart: 
| Complete | In Progress
Sales | 70 | 30
Develop an Asset Disposition Strategy by 2025.
Chart: 
| Complete | In Progress
Sales | 95 | 5
PROCEEDING AS PLANNED
☑ Finalized the Levels of Service as part of the 2025 Comprehensive Asset Management Plan
Chart: 
| Category 1
Complete | 100
COMPLETE
☑ Completed GIS-based mapping layer of municipal assets
Chart: 
| Category 1
Complete | 35
In Progress | 65
Completed technical review and engagement to support finalizing the following plans:
☑ Parks & Trails Master Plan
☑ Facilities Master Plan
 Transportation Master Plan (TMP)
 Active Transportation Strategy (ATS)
 Water/Wastewater Master Plan (WWWMP)
UNDER REVIEW
PROCEEDING AS PLANNED

## Slide 22: COMPLETE COMMUNITIES

## Slide 23
Implement regulatory changes to manage growth which best serves King’s unique landscape.
Update Urban Zoning By-law within 1 year of the OP update.
Complete the Official Plan review and update (to 2051) by 2025 2027.
Conduct the Blue Box Transition by 2025.
Explore opportunities for Commercial Licensing and if approved, implement programs by 2026.
☑ Completed the Growth Management and Employment Lands Strategies
☑ Started work on Natural Heritage Background Report
☑ Integrated Neighbourhood Plan into Official Plan Review
Chart: 
| Complete | In Progress
Sales | 50 | 50
☑ Gathered community input from in-person open house and online public survey
☑ Engaged external stakeholders to inform policy decisions
☑ Developed Commercial Licensing Framework Discussion Paper
Chart: 
| Complete | In Progress
Sales | 60 | 40
☑ Completed transition to provincially-led program
☑ Communicated service changes, gathered feedback, and advocated for residents.
NOT STARTED
PROCEEDING AS PLANNED
PROCEEDING AS PLANNED
SCHEDULED TO START IN 2027
Chart: 
| Category 1
Complete | 100
COMPLETE

## Slide 24
Enrich community well-being and make King the ideal place to live, work and play.
Develop an Action Plan and begin implementation to become an “Age-Friendly Community” by 2026.
Develop and implement a streamlined program that consolidates all existing municipal funding, grant programs, donations, and in-kind contribution requests by 2024.
Represent King’s interest in major external developments within the Township.
Develop and implement an annual Traffic-Safety campaign that runs for (1) month annually.
☑ Key result completed in 2024 reporting year
☑ Monitored and advocated for King in the development of:
Zoning enforcement and illegal land use policies
Expanded rural eligibility for Building Faster Fund
Climate-resilient infrastructure investments in agricultural areas
☑ Engaged 51 businesses exploring investment in King
COMPLETE
PROCEEDING AS PLANNED
Chart: 
PROCEEDING AS PLANNED
PROCEEDING AS PLANNED
☑ Completed Age-Friendly Action Plan
Chart: 
| Category 1
Complete | 85
In Progress | 20
☑ Created the “Safe Streets Campaign” and Launched the Campaign for 4 weeks
☑ Collaborated with York Region Police
☑ Began plan for 2026 annual campaign
Chart: 
| Complete | In Progress
Sales | 75 | 25
Chart: 
| Category 1
Complete | 100
In Progress | 0
100%

## Slide 25
2025 Youth Sticker Design Contest

## Slide 26: SERVICE EXCELLENCE

## Slide 27
Increase data-driven decision making to improve organizational performance
Develop and evolve a Corporate Performance Accountability Program by 2026.
☑ Developed Corporate Performance Accountability Program Administrative Policy
☑ Launched Divisional Service Profiles
☑ Developed Strategic Performance Reporting Procedures
☑ Developed Operational Performance Reporting Procedures
Develop a Digital Transformation Framework and implement Phase 1 by 2025.
☑ Developed and launched the Digital Transformation Framework
☑ Finalized Cyber Security and Risk Management Playbook
☑ Finalized the Data Masterplan
☑ Retained a consultant to validate engagement and develop a forward digital roadmap
PROCEEDING AS PLANNED
COMPLETE
75%
25%
Publish (4) new open-data sets.
☑ Key result completed in 2024 reporting year
Chart: 
| Category 1
Complete | 10
Chart: 
| Complete
Sales | 100
COMPLETE

## Slide 28
2025 Artificial Intelligence Program Recognition
AMTCO’s E. A. Danby Award
MISA’s Excellence in Municipal Systems Award

## Slide 29
Enhance service experience.
Develop and implement a Customer Experience Strategy by 2025.
Reduce “Information Only” Cases by 30%.
Launch (2) new ServiceKING locations for expanded community use and access.
☑ Published ads, posts and reels based on weekly top 3 ServiceKING inquiries
☑ Executed over 100 communications campaigns
☑ Launched appointments through AskKing Zoning Service
☑ Expanded Kingsley knowledge base using York Region service data
Chart: 
| Complete | In Progress
Sales | 100 | 0
☑ Launched two new ServiceKING locations, offering services such as:
Tele-support for ServiceKING and recreation inquiries
In-person service bookings
Sale of garbage tags
90% of all Township application, requests and forms can be submitted in an automated form.
Chart: 
| Category 1
Complete | 100
Chart: 
| Category 1
Complete | 0.8
In Progress | 0.2
PROCEEDING AS PLANNED
COMPLETE
COMPLETE
☑ Key result completed in 2024 reporting year
COMPLETE
☑ Developed Customer Experience Action Plan & Road Map
☑ Received Council endorsement for Customer Experience Strategy

## Slide 30: CSP Performance Report Summary
A Greener Future
Complete Communities
Service Excellence
Sustainable Asset Management
Key Results Status Summary
Legend
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.41 | 0.48 | 0 | 0.07 | 0.04
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.14 | 0.72 | 0 | 0.14 | 0
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.25 | 0.62 | 0 | 0 | 0.13
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.57 | 0.29 | 0.14 | 0
Chart: 
| Complete | Proceeding as Planned | Being Monitored | Under Review | Not Started
Column1 | 0.71 | 0.29 | 0 | 0 | 0

## Slide 31
Communications Plan
Newspaper Half Page Ad
Social Media
Media Release
King.ca

## Slide 32: 2025 (Year 3) Annual Progress Report Strategic Plan Dashboard

## Slide 33: Strategic Plan Dashboard

## Slide 34: Strategic Plan Dashboard

## Slide 35: Strategic Plan Dashboard

## Slide 36
Concluding Remarks

## Slide 37
COUNCIL Q&A